## Major Projects Status Report
University of Virginia
Major Projects Status Report
Project | Scope | Budget (Authorization) [GF Support] | BOV Design Review Status (upcoming actions are shaded) |  |  | Construction
|  |  | Concept/ Site/Design Guidelines | Architect/ Engineer Selection | Schematic Design | Start | Complete
(TBD until contract awarded)
Academic Division / Agency 207
Advanced Research & Technology Building | 84,500 gsf new | 41500000 | n/a, UVaF project | n/a, UVaF project | n/a, UVaF project | TBD | TBD
-38870000
Alderman Rd Residence Area: Hereford First Yr | 120 beds | $12.6 - $14.7M | 2005-06-05 | 2005-11-01 | 2006-03-01 | TBD | TBD
Architect: Wallace Roberts & Todd, LLC |  | -38500000
Address: Philadelphia, PA
Contract Date:
Contractor:
Address:
Alderman Rd Residence Area: Observatory Hill | 160 beds | $12.6 - $14.7M | 2005-06-05 | 2005-11-01 | 2006-03-01 | TBD | TBD
Architect: Hanbury Evans Wright Vlattas |  | -38500000
Address: Norfolk, VA
Contract Date:
Contractor:
Address:
Arts Grounds Parking Garage | 523 cars | 11400000 | 2004-12-01 | 2005-06-01 | 2006-01-01 | TBD | TBD
Architect: Kimley Horn and Associates |  | -10600000
Address: Virginia Beach, VA
Contract Date:
Contractor:
Address:
Bavaro Hall (Ed School Building) | 80,000 gsf new | 37200000 | 2005-03-01 | 2005-06-05 | 2006-03-01 | TBD | TBD
Architect: Robert A.M. Stern Architects, P.C. |  | -32000000
Address: New York, NY
Contract Date:
Contractor:
Address:
Campbell Hall Additions | 14,430 gsf new | 10000000 | 2002-05-01 | 2001-06-01 | 2002-07-01 | TBD | TBD
Architect: SMBW, P.C. |  | -8500000
Address: Richmond, VA | 5,910 gsf ren
Contract Date: August 10, 2001
Contractor:
Address:
Campbell Hall Chiller Expansion | add chiller and cooling towers | 3200000 | n/a, infrastructure with no exterior impact | n/a, < $5M | n/a, infrastructure with no exterior impact | 2005-06-01 | 2006-02-01
Architect: |  | -3200000
Address: |  | [$1.6M GOB]
Contract Date: |  | -3200000
Contractor: Waco, Inc. |  | [$1.6M GOB/ $0.86M GF]
Address: Sandstrom/Covington, VA
Carter-Harrison Research Building (MR-6) | 200,000 gsf new | 84100000 | 2000-06-01 | 2000-06-01 | 2001-02-01 | TBD | TBD
Architect: Henningson, Durham & Richardson |  | -70700000
Address: Alexandria, VA |  | [$24.3M GOB]
Contract Date:
Contractor:
Address:
Cavalier Substation Expansion | increase electrical capacity | 5600000 | n/a, infrastructure with no exterior impact | n/a, originally < $5M | n/a, infrastructure with no exterior impact | 2005-03-01 | 2006-10-01
Architect: |  | -4700000
Address: |  | [$4.7M GOB]
Contract Date: |  | -4700000
Contractor: various |  | [$4.7M GOB]
Address: various
Center for the Arts | 1,600 seat hall art museum 137,000 gsf new | 98000000 | 2004-12-01 | 2006-03-01 | pending | TBD | TBD
Architect: |  | -98000000
Address:
Contract Date:
Contractor:
Address:
Cocke Hall Renovation | 20,000 gsf ren | 9000000 | 2002-12-01 | 2002-09-01 | 2003-08-01 | 2005-03-01 | 2006-12-01
Architect: Schwartz Silver |  | -9000000
Address: Boston, MA |  | [$6M 21st Cent.]
Contract Date: October 30, 2003
Contractor: R.E, Lee
Address: Charlottesville, VA
Environmental Science Field Station (LTER) | 15,151 gsf new | 2788000 | 1998-06-01 | 1999-05-01 | 2001-01-01 | 2004-10-04 | 2006-03-01
Design Builder: McKenzie Construction |  | -2788000
Address: Virginia Beach, VA
Contract Date: June 2004
Fayerweather Hall Renovation | 18,745 gsf ren | 7700000 | 1999-10-01 | 1998-03-01 | 1999-11-01 | 2004-06-01 | 2006-03-01
Architect: Dagit - Saylor Architect |  | -7700000
Address: Philadelphia, PA |  | [$5.362M GOB/ 21st Century]
Contract Date: September 28, 1999
Contractor: Martin Horn
Address: Charlottesville, VA
Gilmer Teaching Labs Renovation | 14,000 gsf ren | 6275000 | n/a, renovation with no exterior impact | 2005-04-05 | n/a, renovation with no exterior impact | 2006-05-01 | 2007-07-01
Architect: Lavigne Associates Architects |  | -5700000
Address: Alexandria, VA |  | [$5.7M GOB]
Contract Date: various
Contractor: various
Address: various
John Paul Jones Arena and Parking | 15,000 seats | 142724000 | 2002-04-01 | 2001-07-01 | 2002-05-01 | 2003-04-01 | 2006-06-01
Architect: VMDO Architects, P.C. | 1,500 cars | -129800000
Address: Charlottesville, VA | N. Grounds connector, Dell, Project Extras
Contract Date: October 2, 2001
Contractor: Barton Malow
Address: Charlottesville, VA
Main Heating Plant Environmental Compliance | Replace/improve 5 boilers | 68200000 | n/a | 2003-05-01 | 2004-04-01 | 2005-04-01 | 2008-09-01
Architect: RMF Engineering, Inc. |  | -39300000
Address: Baltimore, MD |  | [$17.5M 21st Century]
Contract Date: September 2, 2003
Contractor: Frank Lill & Sons
Address: Webster, NY
Medical Education Building | 60,000 to 65,000 gsf new | 30000000 | 2005-06-01 | 2005-11-01 | 2006-09-01 | TBD | TBD
Architect: CO Architects |  | -20700000
Address: Los Angeles, CA
Contract Date:
Contractor:
Address:
Nursing School Building | 30,000 gsf new | 12000000 | 2004-12-01 | 2005-03-01 | 2005-09-01 | TBD | TBD
Architect: Bowie Gridley Architects |  | -12000000
Address: Washington, DC |  | [$6M 21st Cent.]
Contract Date:
Contractor:
Address:
Rouss Hall / Commerce School | 125,000 gsf new | 57000000 | 2002-12-01 | 2002-09-01 | 2003-05-01 | 2005-03-01 | 2008-02-01
Architect: Hartman-Cox Architects | 23,000 gsf ren | -57000000
Address: Washington, DC
Contract Date: March 8, 2005
Contractor: Gilbane
Address: Laurel, MD
South Lawn - A&S Building (Phase 1a) | 108,000 gsf new | 105000000 | 2002-06-01 | 2005-09-30 | 2006-03-01 | TBD | TBD
Architect: Moore Ruble Yudell | 150-200 cars | -78100000
Address: Santa Monica, CA | JPA crossing | [$14.284M GOB]
Contract Date:
Contractor:
Address:
Studio Art Building | 42,000 gsf new | 16700000 | 2003-04-01 | 2003-05-01 | 2004-05-01 | TBD | TBD
Architect: Schwartz/Silver Architects, Inc. |  | -15440000
Address: Boston, MA |  | [$9M 21st Cent.]
Contract Date: November 24, 2003
Contractor:
Address:
University Center | 50,000 gsf new | 15000000 | TBD | 2004-02-01 | TBD | TBD | TBD
Architect: Venturi Scott Brown Assoc. |  | -15000000
Address: Philadelphia, PA
Contract Date:
Contractor:
Address:
Varsity Hall Renovation | 6,000 gsf ren | 2980000 | n/a, renovation with no exterior impact | n/a, < $5M | n/a, renovation with no exterior impact | 2005-09-05 | 2007-12-01
Architect: Train and Partners |  | -2200000
Address: Charlottesville, VA
Contract Date:
Contractor:
Address:
Wilsdorf Hall (formerly MSENT) | 98,040 gsf new | 43383849 | 2001-10-01 | 2001-01-01 | 2002-02-01 | 2003-02-01 | 2006-09-01
Architect: VMDO Architects |  | -43383849
Address: Charlottesville, VA |  | [$7M GOB]
Contract Date: April, 2001
Contractor: Barton Malow
Address: Charlottesville, VA
Medical Center / Agency 209
Clinical Cancer Center | 100,000 gsf new | 55000000 | 2004-10-01 | 2004-10-01 | 2006-03-01 | TBD | TBD
Architect: Zimmer-Gunsul-Frasca Partnership |  | -70700000
Address: Washington, D.C.
Contract Date:
Contractor:
Address:
Hospital Bed Expansion and Infrastructure | 40,000 gsf new | 78000000 | 2005-09-01 | 2005-12-01 | 2006-05-01 | TBD | TBD
Architect: SmithGroup MidAtlantic | 60,000 gsf ren | 0
Address: Washington, D.C.
Contract Date:
Contractor:
Address:
Hospital Expansion | 126,000 gsf new | 99200000 | 2001-06-01 | 2000-06-01 | 2002-05-01 | 2003-01-01 | Aug-05 new
Architect: RTKL | 150,000 gsf ren | -89600000 |  |  |  |  | Dec-06 ren
Address: Baltimore, MD
Contract Date: August 21, 2000
Contractor: Skanska USA Building Inc.
Address: Atlanta, GA
Hospital Link Project | add offices along upper portion of link between University Hospital and West Complex | 4000000 | n/a, renovation with no exterior impact | n/a, < $5M | n/a, renovation with no exterior impact | TBD | TBD
Architect: PSA Dewberry |  | 0
Address:
Contract Date:
Contractor:
Address:
South Chiller Plant Addition | add 4,000 tons of capacity | 15000000 | 2005-11-05 | 2005-11-01 | 2006-03-01 | TBD | TBD
Architect: Affiliated Engineers East, PC |  | -30000000
Address: Chapel Hill, NC
Contract Date:
Contractor:
Address:
Contractor:
Address:
University of Virginia / College at Wise / Agency 246
Crockett Hall Renovation |  | 6500000 | 2002-11-01 | 2000-11-01 | 2006-01-01 | TBD | TBD
Architect: Mitchell Mathews |  | -7133000
Address: Charlottesville, VA |  | [$7.13M 21st Cent.]
Contract Date: February 18, 2003
Contractor:
Address:
Arts Center (formerly Drama Bldg Addition) | Renovations | 11475000 | 2003-05-01 | 2004-09-01 | 2006-05-01 | TBD | TBD
Architect: Bushman Dreyfus Architects | and Additions | -11475000
Address: Charlottesville, VA |  | [$7.475M GOB]
Contract Date: September 28, 2004
Contractor:
Address:
New Main Entrance | Visitor Access Revised Entry Stormwater Mgmt. | 2000000 | n/a, site project | n/a, < $5M | 2006-01-01 | TBD | TBD
Architect: David Hill Studio |  | -2000000
Address: Roanoke, VA
Contract Date:
Contractor:
Address:
New Residence Hall | 120 beds | 7185000 | 2003-05-01 | 2003-07-01 | 2004-02-01 | 2004-08-01 | 2006-03-01
Architect: Ken Ross Architects, Inc. |  | -7185000
Address: Johnson City, TN
Contract Date: October 20, 2003
Contractor: Swope Construction
Address: Blue Field, WVa

## Other Items for BOV Review (hidden)
University of Virginia
Other Items for BOV Review
Description | Frequency | Next Review | Committee | Notes
A/E Selections Less than $5M | Quarterly | 2005-11-01 | B&G
Crispell Drive Easement | Once | 2005-12-05 | B&G
Deed Restriction at EHS | Once | 2005-12-05 | B&G
Progress Report on 2005-06 Goals and Work Plan | Quarterly | 2006-01-01 | B&G
Land Use and Grounds Plans | As needed | 2006-03-01 | B&G
Wise Campus Plan | Once | 2006-01-01 | B&G
Post-Occupancy Report for Special Collections | Once | 2006-02-01 | B&G
Oakhurst Circle Garage Demolition (South Lawn) | Once | 2006-03-01 | B&G | Present when South Lawn design is presented
B-1 Site Building Demolitions (South Lawn) | Once | 2006-03-01 | B&G | Present when South Lawn design is presented
Six Year Plan Submittal Follow-up Report | Biennially | Fall-07 | B&G
Six Year Plan Approval | Biennially | Spring-07 | B&G
General Assembly Follow-up Report | Annually | 2006-05-01 | Finance
Intent to Issue Reolutions | Annually | 2006-05-01 | Finance
Major Projects and Design Status Report | At each meeting | 2006-02-01 | Full
Pavilion Occupancy Status | At each meeting | 2006-02-01 | Full
Professional Services Contracts (In-state vs. Out-of-state) | Quarterly | 2006-02-01 | Full
Formulas:
Next Review = +[Next Review, row above]